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EOLI PROJECT

IBTECH ACTIVITIES FOR PERIOD MAY-2004 TO OCT-2004.

IBTech’s personnel attended the EOLI meeting held in Louvaine la Neuve during May.

Regarding WP1, during june an djuly some meetings were held between IBTech and the UNAM team in order to discuss technical aspects referring to the construction of the pilot plant, particularly those aspects which were relevant to the controlling system.

IBTech provided technical assistance to UNAM team in the procurement of equipment . In fact IBTech was in charge of all equipment procurement activities, including equipment inspection at manufacturer’s site before delivery. 

IBTech coordinate equipment deliveries as well according to the scheduled program.

IBTech also specified and approved all equipment and instrumentation before final acquisition by UNAM team.

Currently all equipment has been delivered to the site where the pilot plant has been erected. The exception is the MCC and PC cabinet, whose specification and acquisition presented some technical problems which were finally solved.

IBTech started the construction of the pilot wastewater treatment plant the second week of August. The construction project was planned to be carried out in four steps:

a) Construction of mobile skid. Tankage and electromechanical equipment mounting. Hydraulic piping instalation.

b) Instalation of field instrumentation. Wiring of all equipment and instruments.

c) Motor Control Center and Computer control system instalation.

d) Precomissioning and comissioning activities.

The skid construction is completely finished. All tankage has been already installed and the piping installation is now terminated.

Electrical and instrumentation wiring has been finished as well, but IBTech is waiting for the MCC and PC cabinet to be delivered in order to finish its installation and to begin with the precomissioning activities.

The comissioning activities should be finished no later than november 19th, 2004.
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